## Output
Activity | Owner | Inputs | Outputs | Tools | Duration | Notes
Set up Excel workbook structure | Financial Analyst | — | Excel workbook with sheet tabs | Microsoft Excel | 1 hour | Create tabs for Assumptions, Product Lines, Regions, Monthly Projections, and Summary Dashboard
Create assumptions input sheet | Financial Analyst | — | Assumptions sheet with variable inputs | Microsoft Excel | 2 hours | Include fields for baseline revenue by product/region, market growth rates by region, capacity expansion factors, new product launch timing and contribution percentages
Define 10 product lines | Data Analyst | — | Product line reference list | Microsoft Excel | 30 minutes | Create product line master list for use across all calculations
Define 5 sales regions | Data Analyst | — | Region reference list (North, East, West, South, Central) | Microsoft Excel | 30 minutes | Create region master list for geographic segmentation
Build monthly projection matrix | Financial Analyst | Product line reference list, Region reference list, Assumptions sheet | Monthly revenue projection by product and region | Microsoft Excel | 4 hours | Create 12-month columns with formulas that reference assumptions for market growth, capacity expansion, and new product contribution
Add market growth rate variables | Financial Analyst | Assumptions sheet | Market growth rate inputs by region | Microsoft Excel | 1 hour | Create adjustable percentage fields for each region's growth assumptions
Add capacity expansion variables | Financial Analyst | Assumptions sheet | Capacity expansion factor inputs | Microsoft Excel | 1 hour | Create adjustable capacity multipliers that can be applied month-by-month to model ramp-ups
Add new product launch variables | Financial Analyst | Assumptions sheet | New product launch timing and contribution inputs | Microsoft Excel | 1.5 hours | Create fields for launch month, product line, region, and expected revenue contribution percentage
Build summary dashboard | Financial Analyst | Monthly revenue projection by product and region | Summary dashboard with key metrics | Microsoft Excel | 2 hours | Create visualizations showing total revenue by month, by product line, by region, and year-to-date totals
Add scenario analysis capability | Financial Analyst | Monthly projection matrix, Assumptions sheet | Scenario comparison framework | Microsoft Excel | 2 hours | Create ability to save and compare multiple assumption scenarios side-by-side
Test model with sample data | Data Analyst | Complete Excel model | Validated model with test results | Microsoft Excel | 1.5 hours | Verify all formulas calculate correctly and model responds properly to assumption changes
Create user documentation | Financial Analyst | Complete Excel model | User guide with instructions | Microsoft Word, Excel | 1.5 hours | Document how to input baseline data, adjust variables, interpret results, and run scenarios
Deliver Excel model to user | Financial Analyst | Validated model, User guide | Wonder Cement Revenue Projection Model (xlsx) | Email, File sharing | 30 minutes | Provide model file and documentation for user to populate with actual baseline data